## Gantt Chart w % Complete
GANTT CHART TEMPLATE |  |  |  | Build better gantt charts with TeamGantt for FREE!
To edit this chart, you must first make a copy. Go to File, the select Make a Copy.
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | SEMANA 1 | SEMANA 2 | SEMANA 3 | SEMANA 4
Mes 1
| Análisis del problema | 2018-03-01 | 1 | 2018-03-06 | 5 | 5 | 0 | Matías | 100%
| Diseño de la solución | 2018-03-30 | 30 | 2018-04-07 | 8 | 6.4 | 1.6 | José | 80%
Mes 2
| Programación del backend (API y lógica) | 2018-04-09 | 9 | 2018-04-25 | 16 | 0 | 16 | Giuseppe | 0
| Desarrollo del front end | 2018-04-09 | 9 | 2018-04-25 | 16 | 0 | 16 | Matías | 0
Mes 3
| Pruebas del sistema | 2018-04-26 | 26 | 2018-05-03 | 7 | 0 | 7 | José | 0
| Validación del proyecto | 2018-05-04 | 4 | 2018-05-11 | 7 | 0 | 7 | Matías | 0

## Manual Chart
CARTA GANTT
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Mes 1
| Análisis del problema | 2026-03-18 | 2026-03-30 | 12 | Matías | 100% | bar: WEEK 1 M to WEEK 2 F; WEEK 4 M to WEEK 4 F; WEEK 10 M to WEEK 10 F
| Diseño de la solución | 2026-03-20 | 2026-04-06 | 16 | Jose | 80% | bar: WEEK 2 M to WEEK 4 F; WEEK 10 M to WEEK 10 F
Mes 2
| Programación del backend (API y lógica) | 2026-04-07 | 2026-05-12 | 35 | Giuseppe | 0% | bar: WEEK 4 M to WEEK 10 F
| Desarrollo del front end | 2026-04-08 | 2026-05-12 | 34 | Matías | 0% | bar: WEEK 4 M to WEEK 10 F
Mes 3
| Pruebas del sistema | 2026-05-12 | 2026-05-22 | 10 | José | 0% | bar: WEEK 4 M to WEEK 4 F; WEEK 10 M to WEEK 11 W
| Validación del proyecto | 2026-05-23 | 2026-06-08 | 15 | Giuseppe | 0% | bar: WEEK 4 M to WEEK 4 F; WEEK 10 M to WEEK 10 F; WEEK 11 W to WEEK 12 F